## Bid Form
Pricing Sheet for Bid 26-012; Prairie View Water Plant #2 Generator Project
Vendor:______________________
Item No. | Item Description | Unit | Approx. Quantity | Unit Price | Total Amount
Base Bid Items
1 | Mobilization | LS | 1 | $ | $
2 | Bonds, Insurance and Permits | LS | 1 | $ | $
3 | Provide and install emergency standby diesel generator, with belly diesel fuel storage tank, automatic transfer switch generator pad, and all required equipment for a fully functional emergency generator system as described in plans and project manual. | LS | 1 | $ | $
4 | Reinforced Concrete Generator Pad, including sidewalk, as shown in the drawings and described in the specifications | LS | 1 | $ | $
5 | Standard Bollards | EA | 5 | $ | $
6 | Provide and install all work shown in construction documents including: conduit and feeders, electrical service equipment upgrades, junction boxes, equipment support rack, and all equipment for a fully functional emergency power system. | LS | 1 | $ | $
Base Bid Items Subtotal |  |  |  | 0
Supplementary Items
S-1 | Additional Excavation and Backfill for Structures | CY | 6 | $____________ (1) $10.00 | $
S-2 | Additional Excavation and Backfill for Utilities | CY | 100 | $____________ (1) $15.00 | $
S-3 | Additional Reinforcing Steel | LF | 60 | $____________ (1) $600.00 | $
S-4 | Additional Structural Concrete | LF | 100 | $____________ (1) $350.00 | $
Supplementary Items Total |  |  |  | $
Water Plant Improvements Total |  |  |  | $
(1) This unit price is intended to be a minimum only. Bidder may not decrease this unit price, however, Bidder may increase this unit price. If applicable, cross out the minimum unit price and write the increased unit price in the space above the minimum price.
CONTRACT TIME:
We will achieve Substantial Completion in ______ calendar days (200 days maximum) from the Notice to Proceed with an additional ______ calendar days (30 maximum) after Substantial Completion to achieve Final Completion.
Completion time includes_________ calendar days (8 days minimum) for adverse weather conditions.
We will achieve Substantial Completion in ______ calendar days (200 days maximum) from the Notice to Proceed with an additional ______ calendar days (30 maximum) after Substantial Completion to achieve Final Completion.
Completion time includes_________ calendar days (8 days minimum) for adverse weather conditions.